## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
s
STORY # 01:
Make Voice Calls
STORY # 02:
Get Last Comm. Data
STORY # 03:
Balance Bonus
STORY # 04:
Update Interface
STORY # 04 - TASK # 01:
Add: Textbox for dest number; Textbox for call duration; Two Buttons to start and end call.
STORY # 04 - TASK # 05:
Add: Button and Popup for Last Comm. Information.
STORY # 03 - TASK # 01:
Update the increase balance function to use the bonus fomula.
STORY # 03 - TASK # 05:
Add the bonus tax to the operator plan.
STORY # 02 - TASK # 01:
Add a generic list of comm. to each phone. Update his other lists to use the new (SMS, Video and Voice).
STORY # 02 - TASK # 05:
Create new function to get last communication made by variable.
STORY # 02 - TASK # 10:
Add a new command, a new service and create DTO's to get this information.
STORY # 10 - TASK # 15:
Tests for Balance Bonus.
STORY # 10- TASK # 10:
Tests for Get Last Comm.
STORY # 10 - TASK # 25:
Test gwt interface for the new services.
STORY # 10 - TASK # 20:
Tests for make voice calls.
STORY # 01 - TASK # 01:
Check requirements to make a voice call. (Before)
STORY # 02 - TASK # 15:
Create a new command to Make a Voice Call between two phones.
STORY # 00 - TASK # 00:
Presentation Task Description
STORY # 00 - TASK # 00:
Service Task Description
STORY # 00 - TASK # 00:
Domain task description
STORY # 02 - TASK # 01:
Distribution Task Description
STORY # 00 - TASK # 00:
JUnit Test - Description
STORY # 01 - TASK # 05:
Update phones states to busy. (Starting)
STORY # 01 - TASK # 10:
Return phones to previous states. (Ending)
STORY # 02 - TASK # 20:
Create two new services. One for process call in the source phone, and other in the destination phone.
STORY # 02 - TASK # 20:
Update the create operator command, the service and the DTO's to use the bonus tax.
STORY # 03 - TASK # 15:
Update the operator constructor to use the new bonus tax in his plan.
STORY # 02 - TASK # 02:
Get the las comm. from the comm. made list by index.
STORY # 05:
Fix bugs from release_3
STORY # 05 - TASK # 01:
Update WSDL to new DTO's and Services.
STORY # 05 - TASK # 05:
Update Application Server WebService.
STORY # 07:
Distribute System
STORY # 06:
Secure Transactions
STORY # 08:
Fault Tolerance
STORY # 05 - TASK # 10:
Fix tax functions.
STORY # 07 - TASK # 01:
Study replication methods and UDDI registry.
STORY # 06 - TASK # 01:
Study secure transactions methods.
STORY # 06 - TASK # 05:
Implements a cipher algorithm on WebService Handlers.
STORY # 08 - TASK # 01:
Study bizantine fault tolerance methods.
STORY # 09 - TASK # 15:
Build a FrontEnd class to handle comm. to replicas.
STORY # 15:
Tests
STORY # 09:
Prototyping
STORY # 09 - TASK # 01:
Registry replicas in jUDDI.
STORY # 09 - TASK # 10:
Exchange versions between replicas.
STORY # 09 - TASK # 05:
Load replicas from jUDDI.
STORY # 02 - TASK # 01:
Update others comm. commands to store the comm. in the new variable.
STORY # 06 - TASK # 10:
Create a new Certificate Authority to manager digital certificates.
STORY # 07 - TASK # 05:
Implements jUDDI registry and load methods based on protoype.
STORY # 08 - TASK # 05:
Implements Quorum protocol based on protoype.
STORY # 07 - TASK # 10:
Update WSDL and DTOs based on protoype.
STORY # 09 - TASK # 20:
Implements Quorum protocol.
STORY # 06 - TASK # 15:
Registry the CA in the jUDDI.
STORY # 06 - TASK # 20:
Saves digital certificates.
STORY # 08 - TASK # 10:
Build a FrontEnd class to based on protoype.
STORY # 09 - TASK # 25: Implements Write services.
STORY # 09 - TASK # 30: Implements Read services.
STORY # 09 - TASK # 35:
Optimize services code.
STORY # 09 - TASK # 40:
Support and Transfer knowledge to implementation team.
STORY # 07 - TASK # 15: Implements Write services based on prototype.
STORY # 07 - TASK # 20: Implements Read services based on prototype.

## Availability Estimate
Availability Estimate
weekday | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T
month | April | [14 empty] | May
day | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22 | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29 | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06 | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13 | 2012-05-14 | 2012-05-15
Resource | Sprint #1 | [6 empty] | Sprint #2 | [6 empty] | Sprint #3 | [6 empty] | Sprint #4 | [6 empty] | Sprint #5 |  | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Alex | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 4 | 0 | 4 | 4 | 0 | 0 | 5 | 7 | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 5 | 5 | 5 | 8 | 0 |  |  | 76
Edgar | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 4 | 0 | 0 | 0 | 2 | 5 | 5 | 3 | 0 | 0 | 0 | 4 | 5 | 6 | 6 | 8 | 0 |  |  | 63
Hugo | 2 | 3 | 2 | 2 | 2 | 0 | 0 | 2 | 3 | 0 | 2 | 2 | 0 | 0 | 5 | 7 | 1 | 5 | 0 | 0 | 0 | 5 | 0 | 5 | 5 | 5 | 8 | 0 |  |  | 66
Loff | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 1 | 7 | 3 | 5 | 0 | 0 | 0 | 1 | 5 | 5 | 5 | 5 | 8 | 0 |  |  | 63
Tiago | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 4 | 5 | 4 | 4 | 2 | 0 | 0 | 2 | 0 | 4 | 4 | 4 | 4 | 0 |  |  | 52
Viteche | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 4 | 0 | 0 | 3 | 5 | 3 | 4 | 4 | 0 | 0 | 2 | 0 | 2 | 3 | 3 | 4 | 0 |  |  | 46
Total per Day | 10 | 6 | 8 | 6 | 7 | 0 | 0 | 11 | 18 | 7 | 18 | 20 | 0 | 0 | 18 | 33 | 21 | 28 | 9 | 0 | 0 | 15 | 9 | 26 | 28 | 28 | 40 | 0 | 0 | 0 | 366
Until the end of the Sprint | 27 | 21 | 13 | 7 | 0 | 0 | 0 | 63 | 45 | 38 | 20 | 0 | 0 | 0 | 91 | 58 | 37 | 9 | 0 | 0 | 0 | 131 | 122 | 96 | 68 | 40 | 0 | 0 | 0 | 0
Total per Sprint | 37 | [6 empty] | 74 | [6 empty] | 109 | [6 empty] | 146 | [6 empty] | 0

## Actual Spent Time
Actual Availability
weekday | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T
month | April | [14 empty] | May
day | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22 | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29 | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06 | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13 | 2012-05-14 | 2012-05-15
Resource | Sprint #1 | [6 empty] | Sprint #2 | [6 empty] | Sprint #3 | [6 empty] | Sprint #4 | [6 empty] | Sprint #5 |  | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Alex | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 6 | 6 | 6 | 2 | 4 | 5 | 6 | 3 | 2 | 2 | 7 | 3 | 0 | 0 | 1 | 0 | 6 | [6 empty] | 63
Edgar | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 8 | 0 | 0 | 0 | 6 | 8 | 8 | 0 | 0 | 1 | 8 | 0 | [6 empty] | 59
Hugo | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 4 | 7 | 8 | 3 | 0 | 8 | 0 | 5 | 4 | 8 | 8 | 2 | 0 | 0 | 5 | 2 | 6 | [6 empty] | 76
Loff | 4 | 0 | 4 | 3 | 0 | 0 | 0 | 1 | 6 | 7 | 2 | 2 | 1 | 6 | 1 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 54
Tiago | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 7 | 1 | 2 | 5 | 0 | 0 | 0 | 5 | 5 | 2 | 0 | 0 | 5 | 7 | 8 | [6 empty] | 60
Viteche | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 7 | 1 | 2 | 2 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 3 | 0 | 6 | [6 empty] | 41
Total per Day | 15 | 2 | 11 | 5 | 0 | 0 | 0 | 17 | 30 | 42 | 16 | 10 | 29 | 12 | 9 | 15 | 29 | 34 | 19 | 0 | 0 | 15 | 17 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 353
Until the end of the Sprint | 18 | 16 | 5 | 0 | 0 | 0 | 0 | 139 | 109 | 67 | 51 | 41 | 12 | 0 | 97 | 82 | 53 | 19 | 0 | 0 | 0 | 43 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Sprint | 33 | [6 empty] | 156 | [6 empty] | 106 | [6 empty] | 58 | [6 empty] | 0

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | STORY # 01: Make Voice Calls | As a mobile user I want to make voice calls so that can communicate with another mobile user. | 13
Done! | STORY # 02: Get Last Com. Data | As a mobile user I want to get the last communication data so that I know who and how I contacted, and how much I spent and the length of the communication. | 3
Done! | STORY # 03: Balance Bonus | As a mobile user I want to receive a balance bonus so that I can have more balance to spent. | 2
Done! | STORY # 04: Update Interface | As a mobile user I want to have a functional interface so that I can easily use my mobile phone. | 5
Done! | STORY # 05: Fix Bugs from Release_3 | Fix all bugs identified on RELEASE_3 | 5
Ongoing | STORY # 06: Secure Transactions | As a operator I want to make secure transactions so that can be protected from dangerous events. | 55
Ongoing | STORY # 07: Distribute System | As a operator I want to have a distributed system so that I can avoid centralized faults and have scalable system. | 21
Ongoing | STORY # 08: Fault Tolerance | As a operator I want to do faultless communications so that I can continue providing my service. | 21
Ongoing | STORY # 09: Prototyping | Create a prototype based on phonebook to implements Distribute System and Fault Tolerance. | 34
Ongoing | STORY # 15: Tests | As a mobile user I want to have all my possible actions tested previously so that dont encounter any obvious error. | 21
As a <user type> I want to <do some action> so that <desired result>
As a <user type> I want to <do some action> so that <desired result>
As a <user type> I want to <do some action> so that <desired result>
As a <user type> I want to <do some action> so that <desired result>
As a <user type> I want to <do some action> so that <desired result>
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## 1st Sprint
|  |  |  | 24 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22
Ideal Execution |  |  |  | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0 | 0 | 0
Total per Day |  |  |  | 11 | 11 | 11 | 7 | 7 | 0 | 0 | 0
STORY # 02: Get Last Com. Data | STORY # 02 - TASK # 02: Function to get last comm. made by index. | Domain | Edgar - Loff | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| STORY # 02 - TASK # 10: Add a new command, service and DTO's. | Service | Edgar - Loff | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
STORY # 03: Balance Bonus | STORY # 03 - TASK # 01: Update the increase balance function. | Domain | Hugo - Hugo | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| STORY # 03 - TASK # 15: Update the operator constructor. | Domain | Hugo - Hugo | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| STORY # 03 - TASK # 05: Add the bonus tax to the operator plan. | Domain | Edgar - Edgar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | M | T | W | R | F | S | S
| STORY # 02 - TASK # 20: Update the create operator command, service and DTO's. | Service | Edgar - Edgar | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | Estimate | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22
STORY # 05: Fix bugs from release_3 | STORY # 05: Update WSDL to new DTO's and Services. | Distribution | Loff - Alex | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Ideal | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0 | 0 | 0
| STORY # 05: Update Application Server WebService. | Distribution | Alex - Loff | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Real | 11 | 11 | 11 | 7 | 7 | 0 | 0 | 0
| STORY # 05: Fix tax functions. | Bug-Fix | Alex - Loff | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Domain | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Service | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Presentation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Testing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | Bug-Fix | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 2nd Sprint
|  |  |  | 24 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29
Ideal Execution |  |  |  | 104 | 83.2 | 62.4 | 41.6 | 20.8 | 7.1054e-15 | 0 | 0
Total per Day |  |  |  | 104 | 79 | 57 | 40 | 37 | 29 | 14 | 0
STORY # 04: Update Interface | STORY # 04 - TASK # 01: Add: Two Textbox and Two Buttons to make voice calls. | Presentation | Loff - Alex | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| STORY # 04 - TASK # 05: Add: Button and Popup for Last Comm. Information. | Presentation | Loff - Alex | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| STORY # 04 - TASK # 10: Debug interface. | Testing | Loff - Alex | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
STORY # 01: Make Voice Calls | STORY # 01 - TASK # 01: Check requirements to make a voice call. (Before) | Domain | Loff - Alex | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STORY # 01 - TASK # 05: Update phones states to busy. (Starting) | Domain | Loff - Alex | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| STORY # 01 - TASK # 10: Return phones to previous states. (Ending) | Domain | Loff - Alex | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 0 |  |  | M | T | W | R | F | S | S
| STORY # 02 - TASK # 15: Create a new command to make a Voice Call between two phones. | Service | Loff - Alex | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | Estimate | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29
| STORY # 02 - TASK # 20: Create two new services. Process call in the source and on destination. | Service | Loff - Alex | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Ideal | 104 | 83.2 | 62.4 | 41.6 | 20.8 | 7.1054e-15 | 0 | 0
[12 empty] | Real | 104 | 79 | 57 | 40 | 37 | 29 | 14 | 0
STORY # 06: Secure Transactions | STORY # 06 - TASK # 01: Study secure transactions methods. | Distribution | Alex - Tiago | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Domain | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| STORY # 06 - TASK # 10: Create a new Certificate Authority to manager digital certificates. | Distribution | Alex - Tiago | 8 | 8 | 8 | 5 | 5 | 3 | 0 | 0 | Service | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
STORY # 07: Distribute System | STORY # 07 - TASK # 01: Study replication methods and UDDI registry. | Distribution | Viteche - Tiago | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Presentation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
STORY # 08: Fault Tolerance | STORY # 08 - TASK # 01: Study bizantine fault tolerance methods. | Distribution | Hugo - Edgar | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
STORY # 09: Prototyping | STORY # 09 - TASK # 01: Registry replicas in jUDDI. | Distribution | Hugo - Edgar | 13 | 8 | 7 | 5 | 5 | 4 | 0 | 0 | Testing | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| STORY # 09 - TASK # 05: Load replicas from jUDDI. | Distribution | Hugo - Edgar | 13 | 8 | 7 | 5 | 5 | 4 | 0 | 0 | Bug-Fix | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| STORY # 09 - TASK # 10: Exchange versions between replicas. | Distribution | Hugo - Edgar | 5 | 5 | 5 | 5 | 2 | 2 | 0 | 0
| STORY # 09 - TASK # 15: Build a FrontEnd class to handle comm. to replicas. | Distribution | Hugo - Edgar | 8 | 8 | 8 | 2 | 2 | 2 | 0 | 0
STORY # 15: Make and test Tests | STORY # 10- TASK # 10: Tests for Get Last Comm. | Testing | Loff - Viteche | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| STORY # 10 - TASK # 15: Tests for Balance Bonus. | Testing | Loff - Viteche | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| STORY # 10 - TASK # 20: Tests for make voice calls. | Testing | Loff - Viteche | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| STORY # 10 - TASK # 25: Test gwt interface for the new services. | Testing | Loff - Viteche | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 0
STORY # 02: Get Last Com. Data | STORY # 02 - TASK # 01: Update others comm. commands to store the comm. in the new variable. | Domain | Loff - Alex | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| STORY # 02 - TASK # 05: Create new function to get last communication made by variable. | Domain | Loff - Alex | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 3rd Sprint
|  |  |  | 24 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06
Ideal Execution |  |  |  | 87 | 69.6 | 52.2 | 34.8 | 17.4 | 0 | 0 | 0
Total per Day |  |  |  | 87 | 79 | 64 | 46 | 25 | 7 | 0 | 0
STORY # 06: Secure Transactions | STORY # 06 - TASK # 20: Saves digital certificates. | Distribution | Alex - Loff | 13 | 13 | 5 | 5 | 0 | 0 | 0 | 0
| STORY # 06 - TASK # 25: CA generates keys. | Distribution | Alex - Loff | 8 | 4 | 2 | 2 | 1 | 0 | 0 | 0
[14 empty] | M | T | W | R | F | S | S
STORY # 07: Distribute System | STORY # 07 - TASK # 05: Implements jUDDI registry and load methods based on protoype. | Distribution | Tiago - Viteche | 8 | 8 | 7 | 2 | 0 | 0 | 0 | 0 |  | Estimate | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-05 | 2012-05-06
| STORY # 07 - TASK # 10: Update WSDL and DTOs based on protoype. | Distribution | Tiago - Viteche | 8 | 8 | 8 | 8 | 8 | 7 | 0 | 0
[12 empty] | Ideal | 87 | 69.6 | 52.2 | 34.8 | 17.4 | 0 | 0 | 0
[12 empty] | Real | 87 | 79 | 64 | 46 | 25 | 7 | 0 | 0
[12 empty] | Domain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Distribution | 87 | 78 | 63 | 45 | 21 | 7 | 0 | 0
STORY # 08: Fault Tolerance | STORY # 08 - TASK # 05: Implements Quorum protocol based on prototype. | Distribution | Hugo - Edgar | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STORY # 08 - TASK # 10: Build a FrontEnd class based on prototype. | Distribution | Hugo - Edgar | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | Bug-Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STORY # 09: Prototyping | STORY # 09 - TASK # 20: Implements Quorum protocol. | Distribution | Hugo - Edgar | 13 | 13 | 13 | 10 | 5 | 0 | 0 | 0
| STORY # 09 - TASK # 25: Implements Write services. | Distribution | Hugo - Edgar | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| STORY # 09 - TASK # 30: Implements Read services. | Distribution | Hugo - Edgar | 13 | 13 | 12 | 6 | 3 | 0 | 0 | 0
| Scrum Master |  |  |  | 1 | 1 | 1 | 4 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 4th Sprint
|  |  |  | 24 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13
Ideal Execution |  |  |  | 63 | 50.4 | 37.8 | 25.2 | 12.6 | 0 | 0 | 0
Total per Day |  |  |  | 63 | 46 | 47 | 15 | 0 | 0 | 0 | 0
STORY # 06: Secure Transactions | STORY # 06 - TASK # 15: Registry the CA in the jUDDI. | Distribution | Team 2 - AL | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| STORY # 06 - TASK # 05: Use a cipher algorithm on WebService Handlers. | Distribution | Team 2 - AL | 4 | 4 | 4 | 4
| STORY #06 - TASK # 06: Handle exceptions in CA side. | Distribution | Team 2 - AL | 2 | 0 | 0 | 2
| STORY #06 - TASK # 07: Prototyping Server and Client side Handlers. | Distribution | Team 2 - AL | 8 | 8 | 8 | 5
| STORY #06 - TASK #08: Implementing Handlers based on prototype. | Distribution | Team 2 - AL | 4 | 4 | 4 | 4
[14 empty] | M | T | W | R | F | S | S
STORY # 07: Distribute System | STORY # 07 - TASK # 15: Implements Write services based on prototype. | Distribution | Tiago - Viteche | 13 | 11 | 5 | [6 empty] | Estimate | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-12 | 2012-05-13
| STORY # 07 - TASK # 20: Implements Read services based on prototype. | Distribution | Tiago - Viteche | 13 | 13 | 13
[12 empty] | Ideal | 63 | 50.4 | 37.8 | 25.2 | 12.6 | 0 | 0 | 0
[12 empty] | Real | 63 | 46 | 47 | 15 | 0 | 0 | 0 | 0
[12 empty] | Domain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Distribution | 63 | 46 | 47 | 15 | 0 | 0 | 0 | 0
[12 empty] | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Bug-Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STORY # 09: Prototyping | STORY # 09 - TASK # 35: Optimize services code. | Distribution | Hugo - Edgar | 8 | 4 | 4
| STORY # 09 - TASK # 40: Support and Transfer knowledge to implementation team. | Distribution | Hugo - Edgar | 8 | 0 | 7
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## 5th Sprint
|  |  |  | 16 | M | T | W | R | F | S | S
Story | Task | Category | Who | 2 | Time to finish task (person/hour)
|  |  |  | Estimate | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20
Ideal Execution |  |  |  | 0 | 0 | 0
Total per Day |  |  |  | 0 | 0 | 0
[14 empty] | M | T | W | R | F | S | S
[13 empty] | Estimate | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-19 | 2012-05-20
[12 empty] | Ideal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Real | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Domain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Service | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Distribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Bug-Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## Check
Fibonnaci | Status | Category | Person
0 | Dropped | Domain | Alex - Alex
0.5 | Done! | Service | Alex - Edgar
1 | Blocked | Presentation | Alex - Hugo
2 | Ongoing | Distribution | Alex - Loff
3 | Planned | Testing | Alex - Tiago
5 |  | Bug-Fix | Alex - Viteche
8 |  |  | Edgar - Alex
13 |  |  | Edgar - Edgar
21 |  |  | Edgar - Hugo
34 |  |  | Edgar - Loff
55 |  |  | Edgar - Tiago
89 |  |  | Edgar - Viteche
∞ |  |  | Hugo - Alex
Hugo - Edgar
Hugo - Hugo
Hugo - Loff
Hugo - Tiago
Hugo - Viteche
Loff - Alex
Loff - Edgar
Loff - Hugo
Loff - Loff
Loff - Tiago
Loff - Viteche
Tiago - Alex
Tiago - Edgar
Tiago - Hugo
Tiago - Loff
Tiago - Tiago
Tiago - Viteche
Viteche - Alex
Viteche - Edgar
Viteche - Hugo
Viteche - Loff
Viteche - Tiago
Viteche - Viteche